## Project tasks
Project name | Mobile Application Development
Project manager | Dean Reid
Project start date | 2023-09-30 09:00
Project finish date | 2024-04-18 17:00
Duration | 144 days
% complete | 0%
Task number | Outline number | Name | Assigned to | Duration | Bucket | Depends on | Start | Finish | % complete | Dependents (after) | Effort | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Priority | Sprint | Goal
1 | 1 | Website Design Brief |  | 144 days |  |  | 2023-10-02 09:00 | 2024-04-18 17:00 | 0% |  | 2334 hours | 0 hours | 2334 hours | No |  |  |  |  | Urgent
2 | 1.1 | Research |  | 6.13 days |  |  | 2023-10-02 09:00 | 2023-10-10 10:00 | 0% |  | 96 hours | 0 hours | 96 hours | No |  |  |  |  | Medium
3 | 1.1.1 | Gather information on clients Goals & Vision | Dean Reid | 4.25 days | To do |  | 2023-10-02 09:00 | 2023-10-06 11:00 | 0% |  | 34 hours | 0 hours | 34 hours | No |  |  |  |  | Medium | Backlog
4 | 1.1.2 | Gather Information on clients Brand and Products | Dean Reid | 4.38 days | To do |  | 2023-10-02 09:00 | 2023-10-06 12:00 | 0% |  | 35 hours | 0 hours | 35 hours | No |  |  |  |  | Medium | Backlog
5 | 1.1.3 | Research Competitor Brands | Dean Reid | 2.25 days | To do |  | 2023-10-05 09:00 | 2023-10-09 11:00 | 0% |  | 18 hours | 0 hours | 18 hours | No |  |  |  |  | Medium | Backlog
6 | 1.1.4 | Present results to client | Dean Reid | 1.13 days | To do |  | 2023-10-09 09:00 | 2023-10-10 10:00 | 0% |  | 9 hours | 0 hours | 9 hours | No |  |  |  |  | Medium | Backlog
7 | 1.2 | Concept Generation |  | 21.13 days |  |  | 2023-10-09 09:00 | 2023-11-07 10:00 | 0% |  | 218 hours | 0 hours | 218 hours | No |  |  |  |  | Medium
8 | 1.2.1 | Clarify Strategy for Brand | Dean Reid | 3.13 days | To do |  | 2023-10-09 09:00 | 2023-10-12 10:00 | 0% |  | 25 hours | 0 hours | 25 hours | No |  |  |  |  | Medium | Backlog
9 | 1.2.2 | Get Client Feedback | Dean Reid | 6.13 days | To do |  | 2023-10-12 09:00 | 2023-10-20 10:00 | 0% |  | 49 hours | 0 hours | 49 hours | No |  |  |  |  | Medium | Backlog
10 | 1.2.3 | Draft Creative Brief | Dean Reid | 6.38 days | To do |  | 2023-10-16 09:00 | 2023-10-24 12:00 | 0% |  | 51 hours | 0 hours | 51 hours | No |  |  |  |  | Medium | Backlog
11 | 1.2.4 | Create Concept Art | Dean Reid | 9.5 days | To do |  | 2023-10-23 09:00 | 2023-11-03 13:00 | 0% |  | 76 hours | 0 hours | 76 hours | No |  |  |  |  | Medium | Backlog
12 | 1.2.5 | Get Clients approval of brief and concept | Dean Reid | 2.13 days | To do | 14FS | 2023-11-03 09:00 | 2023-11-07 10:00 | 0% |  | 17 hours | 0 hours | 17 hours | No |  |  |  |  | Medium | Backlog
13 | 1.3 | Graphics Design |  | 19 days |  |  | 2023-10-31 09:00 | 2023-11-24 17:00 | 0% |  | 181 hours | 0 hours | 181 hours | No |  |  |  |  | Medium
14 | 1.3.1 | Review Brand Graphics | Dean Reid | 1.13 days | To do |  | 2023-10-31 09:00 | 2023-11-01 10:00 | 0% | 12FS | 9 hours | 0 hours | 9 hours | No |  |  |  |  | Medium | Backlog
15 | 1.3.2 | Get Colours for website | Dean Reid | 1.13 days | To do |  | 2023-10-31 09:00 | 2023-11-01 10:00 | 0% |  | 9 hours | 0 hours | 9 hours | No |  |  |  |  | Medium | Backlog
16 | 1.3.3 | Research Fonts for use | Dean Reid | 1.13 days | To do |  | 2023-10-31 09:00 | 2023-11-01 10:00 | 0% |  | 9 hours | 0 hours | 9 hours | No |  |  |  |  | Medium | Backlog
17 | 1.3.4 | Research Compatability with Integrating other software | Dean Reid | 8.25 days | To do |  | 2023-10-31 09:00 | 2023-11-10 11:00 | 0% |  | 66 hours | 0 hours | 66 hours | No |  |  |  |  | Medium | Backlog
18 | 1.3.5 | Design CSS for Website | Dean Reid | 11 days | To do |  | 2023-11-10 09:00 | 2023-11-24 17:00 | 0% |  | 88 hours | 0 hours | 88 hours | No |  |  |  |  | Medium | Backlog
19 | 1.4 | Web Design |  | 64.5 days |  |  | 2023-11-13 09:00 | 2024-02-09 13:00 | 0% | 25FS | 817 hours | 0 hours | 817 hours | No |  |  |  |  | Medium
20 | 1.4.1 | Create basic HTML template | Dean Reid | 49.38 days | To do |  | 2023-11-13 09:00 | 2024-01-19 12:00 | 0% | 21FS | 395 hours | 0 hours | 395 hours | No |  |  |  |  | Medium | Backlog
21 | 1.4.2 | Integrate CSS with HTML Template | Dean Reid | 9.13 days | To do | 20FS | 2024-01-19 12:00 | 2024-02-01 13:00 | 0% |  | 73 hours | 0 hours | 73 hours | No |  |  |  |  | Medium | Backlog
22 | 1.4.3 | Design PHP Code | Dean Reid | 24.88 days | To do |  | 2023-12-18 09:00 | 2024-01-19 16:00 | 0% | 23FS | 199 hours | 0 hours | 199 hours | No |  |  |  |  | Medium | Backlog
23 | 1.4.4 | Design SQL Code | Dean Reid | 14.63 days | To do | 22FS | 2024-01-19 16:00 | 2024-02-09 13:00 | 0% |  | 117 hours | 0 hours | 117 hours | No |  |  |  |  | Medium | Backlog
24 | 1.4.5 | Speak to client about any issues and an eta of completion | Dean Reid | 4.13 days | To do |  | 2023-12-11 09:00 | 2023-12-15 10:00 | 0% |  | 33 hours | 0 hours | 33 hours | No |  |  |  |  | Medium | Backlog
25 | 1.5 | Review |  | 4.25 days |  | 19FS | 2024-02-09 13:00 | 2024-02-15 15:00 | 0% |  | 86 hours | 0 hours | 86 hours | No |  |  |  |  | Medium
26 | 1.5.1 | Check for code errors | Dean Reid | 4.25 days | To do |  | 2024-02-09 13:00 | 2024-02-15 15:00 | 0% |  | 34 hours | 0 hours | 34 hours | No |  |  |  |  | Medium | Backlog
27 | 1.5.2 | Present Pre-Tested Draft | Dean Reid | 3.13 days | To do |  | 2024-02-09 13:00 | 2024-02-14 14:00 | 0% |  | 25 hours | 0 hours | 25 hours | No |  |  |  |  | Medium | Backlog
28 | 1.5.3 | Speak to customer and find out concernes | Dean Reid | 3.38 days | To do |  | 2024-02-09 13:00 | 2024-02-14 16:00 | 0% |  | 27 hours | 0 hours | 27 hours | No |  |  |  |  | Medium | Backlog
29 | 1.6 | Testing |  | 49 days |  |  | 2024-02-12 09:00 | 2024-04-18 17:00 | 0% |  | 936 hours | 0 hours | 936 hours | No |  |  |  |  | Medium
30 | 1.6.1 | Browsers | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
31 | 1.6.2 | Screens | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
32 | 1.6.3 | Tablets | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
33 | 1.6.4 | Mobiles | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
34 | 1.6.5 | User Registration | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
35 | 1.6.6 | User Login/Logout | Dean Reid | 6 days | To do |  | 2024-02-12 09:00 | 2024-02-19 17:00 | 0% |  | 48 hours | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
36 | 1.6.7 | Home Page | Dean Reid | 6 days | To do |  | 2024-02-12 09:00 | 2024-02-19 17:00 | 0% |  | 48 hours | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
37 | 1.6.8 | Product Page | Dean Reid | 6 days | To do |  | 2024-02-12 09:00 | 2024-02-19 17:00 | 0% |  | 48 hours | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
38 | 1.6.9 | Products | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
39 | 1.6.10 | Comments | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
40 | 1.6.11 | Admin Registration | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
41 | 1.6.12 | Contact Form | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
42 | 1.6.13 | Ban Accounts | Dean Reid | 5 days | To do |  | 2024-02-12 09:00 | 2024-02-16 17:00 | 0% |  | 40 hours | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
43 | 1.6.14 | Fix anything and go through code for security issues | Dean Reid | 13 days | To do |  | 2024-02-12 09:00 | 2024-02-28 17:00 | 0% | 44FS | 104 hours | 0 hours | 104 hours | No |  |  |  |  | Medium | Backlog
44 | 1.6.15 | Rollout to customers | Dean Reid | 36 days | To do | 43FS | 2024-02-29 09:00 | 2024-04-18 17:00 | 0% |  | 288 hours | 0 hours | 288 hours | No |  |  |  |  | Medium | Backlog